## README
VLM Distillation — Phase-0 Paper Sprint Tracker
Submission target | ARR May cycle, internal cutoff 2026-05-22
Pair | Qwen/Qwen2.5-VL-7B-Instruct -> Qwen/Qwen2-VL-2B-Instruct
Branch | phase-0-paper-sprint
Plan | phase_0_sprint_plan.md
Sheet | What it's for
Runs | One row per training run. Edit status/wall_clock/notes as runs complete. Yellow = planned, Red = ablation.
Results | Long-format (run x benchmark) score table. Fill the `score` column after each VLMEvalKit run.
Main_Table | Pivoted view for the paper. Uses VLOOKUP into Results — DON'T edit cells, edit Results.
UMI | Per-pair Unit-Mismatch Index from scripts/compute_umi.py output. Copy the JSON fields into the row.
Compute_Log | Daily compute & API spend vs the sprint plan. Track to avoid running out of budget mid-week.
Workflow
1 | Edit `Runs` to mark a run as in-progress / done.
2 | After eval finishes, fill the four/eight/twelve `score` rows for that run in `Results`.
3 | `Main_Table` updates automatically. Decide go/no-go at end of Day 6 using `Avg_fast` column.
4 | Add new runs by appending to `Runs` AND duplicating its result rows in `Results`.
5 | If you change the schema, re-run `python3 scripts/make_experiment_tracker.py` (note: overwrites).
Decision criterion (from phase_0_sprint_plan.md)
Submit | Unit-Aligned >= max(EM-KD-only, SRE-only) - 0.3 pts averaged AND > CE-only avg
Reframe | Unit-Aligned < CE-only -> rewrite as robustness/negative-result paper for a workshop
Abandon sprint | All KD methods < CE-only by >= 1 pt -> add Qwen3-VL pair, target ARR June

## Runs
run_id | method | category | kd_loss_type | extra_args | script | teacher | student | lora_r | lora_alpha | lr | per_device_bs | grad_accum | epochs | percent_data | seed | max_len | status | start_date | end_date | wall_clock_h | ckpt_path | final_step | notes
ce_only_run1 | CE-only | baseline | ce_only |  | script_train/ce_only/train_qwen25_teacher_7b_qwen2_student_2b_ce_only.sh | Qwen/Qwen2.5-VL-7B-Instruct | Qwen/Qwen2-VL-2B-Instruct | 64 | 64 | 1e-5 | 1 | 8 | 1 | 0.15 | 1337 | 2048 | planned
emkd_run1 | EM-KD-only | single-side | emkd | em_kd_alpha=0.5, beta=0.25, gamma=25.0, T=1.0 | script_train/em_kd/train_qwen25_teacher_7b_qwen2_student_2b_emkd.sh | Qwen/Qwen2.5-VL-7B-Instruct | Qwen/Qwen2-VL-2B-Instruct | 64 | 64 | 1e-5 | 1 | 8 | 1 | 0.15 | 1337 | 2048 | planned
sre_run1 | SRE-only | single-side | sre | layer_mapping=[27], sre_use_projector=True, sre_geom_loss_weight=50 | script_train/sre/train_qwen25_teacher_7b_qwen2_student_2b_sre.sh | Qwen/Qwen2.5-VL-7B-Instruct | Qwen/Qwen2-VL-2B-Instruct | 64 | 64 | 1e-5 | 1 | 8 | 1 | 0.15 | 1337 | 2048 | planned
unit_aligned_run1 | Unit-Aligned | joint | unit_aligned | layer_mapping=[27], joint_ce=0.5, joint_emkd=1.0, joint_sre=1.0 | script_train/unit_aligned/train_qwen25_teacher_7b_qwen2_student_2b_unit_aligned.sh | Qwen/Qwen2.5-VL-7B-Instruct | Qwen/Qwen2-VL-2B-Instruct | 64 | 64 | 1e-5 | 1 | 8 | 1 | 0.15 | 1337 | 2048 | planned
unit_aligned_noproj_ablation | Unit-Aligned (no projector) | ablation | unit_aligned | sre_use_projector=False (fallback to crop) | script_train/unit_aligned/train_..._unit_aligned.sh + --sre_use_projector false | Qwen/Qwen2.5-VL-7B-Instruct | Qwen/Qwen2-VL-2B-Instruct | 64 | 64 | 1e-5 | 1 | 8 | 1 | 0.15 | 1337 | 2048 | planned

## Results
run_id | method | suite | dataset | score | n_samples | judge_model | eval_hours | judge_usd | eval_date | notes
ce_only_run1 | CE-only | fast_signal | MMBench_DEV_EN
ce_only_run1 | CE-only | fast_signal | MMStar
ce_only_run1 | CE-only | fast_signal | MMMU_DEV_VAL
ce_only_run1 | CE-only | fast_signal | MathVista_MINI
emkd_run1 | EM-KD-only | fast_signal | MMBench_DEV_EN
emkd_run1 | EM-KD-only | fast_signal | MMStar
emkd_run1 | EM-KD-only | fast_signal | MMMU_DEV_VAL
emkd_run1 | EM-KD-only | fast_signal | MathVista_MINI
sre_run1 | SRE-only | fast_signal | MMBench_DEV_EN
sre_run1 | SRE-only | fast_signal | MMStar
sre_run1 | SRE-only | fast_signal | MMMU_DEV_VAL
sre_run1 | SRE-only | fast_signal | MathVista_MINI
unit_aligned_run1 | Unit-Aligned | fast_signal | MMBench_DEV_EN
unit_aligned_run1 | Unit-Aligned | fast_signal | MMStar
unit_aligned_run1 | Unit-Aligned | fast_signal | MMMU_DEV_VAL
unit_aligned_run1 | Unit-Aligned | fast_signal | MathVista_MINI
unit_aligned_noproj_ablation | Unit-Aligned (no projector) | fast_signal | MMBench_DEV_EN
unit_aligned_noproj_ablation | Unit-Aligned (no projector) | fast_signal | MMStar
unit_aligned_noproj_ablation | Unit-Aligned (no projector) | fast_signal | MMMU_DEV_VAL
unit_aligned_noproj_ablation | Unit-Aligned (no projector) | fast_signal | MathVista_MINI
ce_only_run1 | CE-only | main_table | MMVet
ce_only_run1 | CE-only | main_table | AI2D_TEST_NO_MASK
ce_only_run1 | CE-only | main_table | ChartQA_TEST
ce_only_run1 | CE-only | main_table | POPE
emkd_run1 | EM-KD-only | main_table | MMVet
emkd_run1 | EM-KD-only | main_table | AI2D_TEST_NO_MASK
emkd_run1 | EM-KD-only | main_table | ChartQA_TEST
emkd_run1 | EM-KD-only | main_table | POPE
sre_run1 | SRE-only | main_table | MMVet
sre_run1 | SRE-only | main_table | AI2D_TEST_NO_MASK
sre_run1 | SRE-only | main_table | ChartQA_TEST
sre_run1 | SRE-only | main_table | POPE
unit_aligned_run1 | Unit-Aligned | main_table | MMVet
unit_aligned_run1 | Unit-Aligned | main_table | AI2D_TEST_NO_MASK
unit_aligned_run1 | Unit-Aligned | main_table | ChartQA_TEST
unit_aligned_run1 | Unit-Aligned | main_table | POPE

## Main_Table
Main Paper Table (Method x Benchmark)
Edit Results sheet; this table refreshes via VLOOKUP. Blank cells mean no result yet.
Method | MMBench_DEV_EN | MMStar | MMMU_DEV_VAL | MathVista_MINI | MMVet | AI2D_TEST_NO_MASK | ChartQA_TEST | POPE | Avg_fast (4) | Avg_main (8)
CE-only
EM-KD-only
SRE-only
Unit-Aligned
Delta (Unit-Aligned - max(EM-KD, SRE)) — submit if >= -0.3

## UMI
pair_name | teacher | student | vocab_jaccard_on_corpus | student_vocab_used | teacher_vocab_used | vision_token_ratio_mean | umi_text_component | umi_vision_component | umi | response_sample | image_sample | seed | computed_date | notes
qwen25_to_qwen2 | Qwen/Qwen2.5-VL-7B-Instruct | Qwen/Qwen2-VL-2B-Instruct
(future pairs for ARR June: Qwen3-VL-8B->Qwen2.5-VL-3B, LLaVA-OV-7B->Qwen2.5-VL-3B)

## Compute_Log
date | day_num | planned_task | actual_task | gpu_hours_used_today | gpu_hours_cumulative | judge_usd_today | judge_usd_cumulative | blocker | notes
2026-05-15 | 1 | Code fixes + UMI computation + paper skeleton stub
2026-05-16 | 2 | Teacher logit cache + CE-only training launch + paper skeleton
2026-05-17 | 3 | EM-KD-only training launch + VLMEvalKit setup
2026-05-18 | 4 | SRE-only training launch + CE-only fast_signal eval
2026-05-19 | 5 | Unit-Aligned training launch + EM-KD-only fast_signal eval
2026-05-20 | 6 | Unit-Aligned eval + SRE-only eval + ablation run
2026-05-21 | 7 | Tables + write results/discussion + camera-ready polish
2026-05-22 | 8 | Final reproducibility check + SUBMIT